## Sheet1
WEEKLY STATUS REPORT - Week 2
Employee | Lien Chen
From: | 2014-06-23
To: | 2014-06-27
PLAN FOR THIS WEEK | STATUS
Study existing R prepayment model code | In Progress
Develop some toy R programs | Done
Read prepayment model papers | Done
ACTIVITIES COMPLETED THIS WEEK | DELIVERABLES
Functional design for fitting model | Functional Design Description - Fitting
Recode the prepayment model
- default | fit_default_model.R
func_default.R
- turnover | fit_turnover_model.R
func_turnover.R
Check Fund Perpormance daily report | Check reports and send out message for team members
ACTIVITIES IN PROCESS | NEXT ACTION | DUE DATE
Recode the prepayment model
- refinancing | still working on | 2014-07-04
ACTIVITIES TO BE STARTED NEXT WEEK
Study existing R prepayment model code
Finish recode for fitting model
Design for tracking model