## Sheet1
WEEKLY STATUS REPORT - Week 3
Employee | Lien Chen
From: | 2014-06-30
To: | 2014-07-03
PLAN FOR THIS WEEK | STATUS
Study existing R prepayment model code | Done
Finish recode for fitting model | Done
Design for tracking model | In Progress
ACTIVITIES COMPLETED THIS WEEK | DELIVERABLES
Reseach on the ppm model input | Study report (section three: Model Input)
Review the prepayment model
- default | fit_refi_model.R
fit_refi_readDB.R
fit_refi_economic_readDB.R
func_refinancing.R
Debug previous fiiting model | Model Parameters Correction Spreadsheet
Check Fund Perpormance daily report | Check reports and send out message for team members
ACTIVITIES IN PROCESS | NEXT ACTION | DUE DATE
Design for tracking model | still working on | 2014-07-10
ACTIVITIES TO BE STARTED NEXT WEEK
Rewrite the tracking model