## Sheet1
WEEKLY STATUS REPORT - Week 5
Employee | Lien Chen
From: | 2014-07-14
To: | 2014-07-18
PLAN FOR THIS WEEK | STATUS
Design for tracking model | Done
Rewrite the tracking model | In Progress
ACTIVITIES COMPLETED THIS WEEK | DELIVERABLES
design tracking model | tracking result plot
1.track the fitting result for 4 components
2.analyzed fitting error comtribution of the components
3.come up with some model improve ideas(data range, media effect, spline function)
media effect analysis | media effect study report
1.analyzed media effect time serise
2.fix media effect "jump up" problem when mortgage rate keep constant
work on CCMQuantLib | CCMUtilDatabaseToProtoBuffer: HistoricalRatesGen.cs
1.extend the 30 yrs mortgage rate input range from 2013 to 2001, get rid of the "fixed period" problem for 6 rate input
Check Fund Perpormance daily report | Check reports and send out message for team members
ACTIVITIES IN PROCESS | NEXT ACTION | DUE DATE
media effect analysis | still working on | 2014-07-25
work on CCMQuantLib | still working on | -
ACTIVITIES TO BE STARTED NEXT WEEK
-