## Sheet1
WEEKLY STATUS REPORT - Week 6
Employee | Lien Chen
From: | 2014-07-21
To: | 2014-07-25
PLAN FOR THIS WEEK | STATUS
Rewrite the tracking model | Done
Media effect analysis | Done
Credit availability factor research | In Progress
ACTIVITIES COMPLETED THIS WEEK | DELIVERABLES
Credit availability factor research
1.HPA measure shows a higher prediction smm than actual in recent 2 yrs. Due to much more strict underwriting criteria, we might need to find a credit availability other than HPA. | media_effect_step3_hpa.xlsx
2.Get a right model shape by using Purchase Index instead of HPA, though MBAVPRCH index is sensitive to mortgage rate. | media_effect_step4_MBAVPRCH.xlsx
3.Get a less rate-sensitive measure for credit availability by constructing a distribution of FICO score in all purchases. | loan_level_result.xlsx media_effect_step5_fico%change.xlsx
4. Chose to use FNM and FHL combined % purchase series after compare data in FNM, FHL separately and combined. | loan_level_result_Fannie.csv loan_level_result_Freddie.csv media_effect_step5_fico%change_compare.xlsx
Check Fund Performance daily report | Check reports and send out message for team members
ACTIVITIES IN PROCESS | NEXT ACTION | DUE DATE
Credit availability factor research | still working on | 2014-08-01
work on CCMQuantLib | still working on | -
ACTIVITIES TO BE STARTED NEXT WEEK
-