## Sheet1
WEEKLY STATUS REPORT - Week 7
Employee | Lien Chen
From: | 2014-07-28
To: | 2014-08-01
PLAN FOR THIS WEEK | STATUS
Credit availability factor research | In Progress
Check tacking output from R code and C++ | In Progress
ACTIVITIES COMPLETED THIS WEEK | DELIVERABLES
Update Prepayment fitting model
1.changed smooth.spline function into hermite cubic spline for all four sub-components, make the interpolation consistent in both R and C++ codes | ppmRCode_2.0
2.added result ploting function for every factor in each component model
Check tracking result with Neo, make sure both side provide correct result.
1. fixed interpolation error and time lag problem in Curtail, Default, Turnover models. Results of these 3 sub-models are the same in R and C++. | Compare_result_AE5463_0724.xlsx
2. added boundary value for each factor(when factor value is higher than the max knot, or lower than the min) | Compare_result_AE5463_0730.xlsx
Check Fund Performance daily report | Check reports and send out message for team members
ACTIVITIES IN PROCESS | NEXT ACTION | DUE DATE
Credit availability factor research | still working on | 2014-08-08
Check tracking result for refinancing with Neo | still working on | 2014-08-08
ACTIVITIES TO BE STARTED NEXT WEEK
-